## Goal 1 Actions
Action Description | Status | Comments, Challenges, and/or Modifications | Hyperlinks, Examples, Resources That Can Be Shared | Additional Notes
Outcome 1.1: Americans are educated about and understand the experience of family caregiving. | - | - | - | -
The Indian Health Service (IHS) will, in late 2022, publish a blog on the IHS website that addresses the role of caregivers. | Complete | A social media toolkit for National Caregiver Month (November 2022) was developed, and content was distributed on IHS social media platforms in November and December. A November Facebook post ranked in the top 10 for engagement. Two additional social media posts referencing caregivers were distributed in September 2022, including promoting the National Strategy to Support Family Caregivers report. | N/A | This work continued in 2023.
IHS will identify caregiver content for the IHS Alzheimer’s Grant Program website that provides information about caregiving, as well as resource links for caregivers in 2022. | Complete | Caregiver content and resource links are now posted on two pages of the IHS website, including the new Alzheimer’s Grant Program site. | N/A | This work continued in 2023.
Outcome 1.3: Outreach to family caregivers is improved. | - | - | - | -
IHS will collaborate in 2022 with the CDC-funded New York University BOLD Center of Excellence on Early Detection of Dementia on the adaptation of an early recognition toolkit for use in IHS, tribal, and urban Indian health programs with the goal of improving early detection of dementia and identification of caregivers. | In process | IHS continues to collaborate with the NYU BOLD Public Health Center of Excellence on Dementia Diagnosis to increase the use of simple, valid tools to detect cognitive impairment and guide newly diagnosed individuals to services and supports. | N/A | N/A
Outcome 1.4: Family caregiving — and caregivers — are embedded in federal, state, territorial, tribal, and local planning. | - | - | - | -
IHS will award up to 5 tribal grants and up to 3 IHS program awards in 2022 to develop a comprehensive approach to addressing dementia in tribal communities, including attention to the needs of caregivers. | Complete | IHS awarded funding to all four grant applicants from tribal and urban Indian health clinics and systems with funding start dates of September 2022 for a two-year funding total of $1.3 million. There were no IHS program award applications for 2022. | N/A | N/A
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support. | - | - | - | -
IHS will continue to collaborate with the Northwest Portland Area Indian Health Board in a once-monthly ECHO session aimed at increasing the effectiveness of caregiver support. | Complete | Two new IHS-funded ECHO series have been developed with the Northwest Portland Indian Health Board (NPAIHB) Indian Country ECHO program. The monthly Dementia Clinical ECHO series began in May 2023, and the curriculum incorporates caregiver support. The monthly Caregiver Support ECHO will begin in June 2023. | N/A | N/A
IHS will collaborate with the CDC-funded New York University BOLD Center of Excellence on Early Detection of Dementia on the adaptation of an early recognition toolkit for use in IHS, tribal, and urban Indian health programs with the goal of improving early detection of dementia and identification of caregivers in 2022. | In process | IHS continues to collaborate with the NYU BOLD Public Health Center of Excellence on Dementia Diagnosis to increase the use of simple, valid tools to detect cognitive impairment and guide newly diagnosed individuals to services and supports. | N/A | N/A
push deliverable to 2025

## Goal 2 Actions
Action Description | Status | Comments, Challenges, and/or Modifications | Hyperlinks, Examples, Resources That Can Be Shared | Additional Notes
Outcome 2.1: Family caregivers are recognized as essential partners in the care teams of the person(s) to whom they are providing support. | - | - | - | -
IHS will assess the potential impact on family caregivers of grants and program awards made through the IHS Alzheimer’s Grants Program in 2022. | In process | Caregiving support is identified as one of five key drivers of comprehensive dementia care in IHS Alzheimer’s funding opportunities. Assessment of the impact on family caregivers of the 2022 grantees is underway. | N/A | N/A
IHS will identify requirements for EHR capability that will support the caregiver role through the IHS Health Information Technology (HIT) Modernization Initiative in 2022. | In process | IHS has begun an analysis of EHR capability that will support the caregiver role for incorporation into the IHS Health Information Technology Modernization Initiative. | N/A | N/A
Outcome 2.2: Where appropriate, identifying services and supports needs for caregivers consistently starts with a review of family caregiver strengths and preferences using evidence-based assessments. | - | - | - | -
IHS will work through the IHS Health Information Technology (HIT) Modernization initiative in 2022 to identify family and kin caregivers in structured fields in the EHR of individuals receiving care. | In process | IHS has begun an analysis of EHR capability that will support the caregiver role for incorporation into the IHS Health Information Technology Modernization Initiative. | N/A | N/A
Outcome 2.5: The education curricula of professionals who will potentially work with family caregivers include specific topics and coursework designed to ensure they have the skills to do so effectively. | - | - | - | -
IHS training plan in support of the Alzheimer’s Grants Program will include training and education in support of caregivers and the caregiver role as an essential component of care for individuals living with dementia in 2022. | In process | Caregiver support was incorporated into the curriculum of the Dementia Clinical ECHO series provided by the Northwest Portland Indian Health Board (NPAIHB) Indian Country ECHO program. In June 2023, the monthly Dementia Caregiver ECHO series will begin. Acquisition planning is underway for the IHS Alzheimer’s Grants Program training and education support. | N/A | N/A

## Goal 3 Actions
Action Description | Status | Comments, Challenges, and/or Modifications | Hyperlinks, Examples, Resources That Can Be Shared | Additional Notes
Outcome 3.1: Person- and family-centered, trauma-informed, and culturally appropriate caregiver services and supports are accessible for all family caregivers. | - | - | - | -
IHS will develop a training program over the next year for caregiver coach/support provided by public health nursing and community health representatives, based in the evidence of REACH (Resources to Enhance Alzheimer’s Caregiver Health). | In process | IHS is examining existing models of caregiver coaching, interventions, and support for adaptation and use by IHS, tribal, and urban Indian health program staff in support of caregivers of individuals living with dementia. | N/A | N/A
Outcome 3.3: A range of evidence-based, education, counseling, and peer support services are available to family caregivers. | - | - | - | -
IHS will develop a training program for caregiver coach/support provided by public health nursing and community health representatives, based in the evidence of REACH over the next year. | In process | IHS is examining existing models of caregiver coaching, interventions, and support for adaptation and use by IHS, tribal, and urban Indian health program staff in support of caregivers of individuals living with dementia. | N/A | N/A

## Goal 5 Actions
Action Description | Status | Comments, Challenges, and/or Modifications | Hyperlinks, Examples, Resources That Can Be Shared | Additional Notes
Outcome 5.1: A national infrastructure will exist to support the collection of population-based data, using standardized wording of the definition of family caregiving and standardized wording of questions that address the core characteristics of the family caregiving experience. | - | - | - | -
IHS will work through the IHS Health Information Technology (HIT) Modernization initiative in 2023 to identify family and kin caregivers in structured fields in the EHR of individuals receiving care. | In process | IHS has begun an analysis of EHR capability that will support the caregiver role for incorporation into the IHS Health Information Technology Modernization Initiative. | N/A | N/A
IHS will identify requirements for EHR capability that will support the caregiver role through the IHS Health Information Technology (HIT) Modernization Initiative in 2023. | In Process | IHS has begun an analysis of EHR capability that will support the caregiver role for incorporation into the IHS Health Information Technology Modernization Initiative. | N/A | N/A
Outcome 5.3: Promising and evidence-informed practices are promoted, translated, and disseminated to support family caregivers in the delivery of health care and social services. | - | - | - | -
IHS will continue to collaborate with the Northwest Portland Area Indian Health Board in a once-monthly ECHO session aimed at increasing the effectiveness of caregiver support. | Complete | Two new IHS-funded ECHO series have been developed with the Northwest Portland Indian Health Board (NPAIHB) Indian Country ECHO program. The monthly Dementia Clinical ECHO series began in May 2023. | Dementia Caregiver Support ECHO | N/A

## ACF New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## ACL New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action | CIP/ONA | By September 2024, 10 NWD state grantees will develop a strategic plan to address identified individual and caregiver access challenges and service or population gaps, based on completed comprehensive mapping analysis, to strengthen the state's role in improving a coordinated access system. |  | Ami Patel, ACL
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action | ONA | All states will complete their caregiver mapping exercises by September 30, 2023; Support for caregiver mapping provided on June all-grantee call and July 1:1 calls. |  | Joseph Lugo, ACL
Proposed New Action
Proposed New Action

## AmeriCorps New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## CDC New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action |  | Stakeholder outreach on
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## CFPB New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action | Older Americans | Stakeholder outreach and presentations discussing the financial costs of caregiving (direct and indirect), and how to identify and address consumer financial protection risks (ACL-SMP/SHIP/MIPPAA conference, N. American Collection Agency Regulators Association, National Consumer Law Center, NEI3A-SHIP/TA). |  | Beverly.yang@cfpb.gov
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action | Older Americans | Series of webinars for caregivers and direct service providers on consumer rights, e.g., regarding fraud prevention and response, inaccurate medical bills, and invalid nursing home debt collection against caregivers (AASC, ElderSafe) |  | Beverly.yang@cfpb.gov
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action | Older Americans | Series of webinars for caregivers and direct service providers on consumer rights, e.g., regarding fraud prevention and response, inaccurate medical bills, and invalid nursing home debt collection (ElderSafe) |  | Beverly.yang@cfpb.gov
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action | Older Americans | Research (ongoing and planned) on caregiver / care recipient demographics incl. income source, insurance coverage, relationship - familial, informal, or legal (e.g., friend or grandchild, help writing checks, representative payee, or power of attorney), savings and credit/financial wellness measures, in collaboration with SSA, ASPE, etc. |  | Beverly.yang@cfpb.gov
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action | Older Americans | Completed and planned webinars for caregiver intermediaries (Consumer Voice, ElderSafe, NEI3A, National Academy of Elder Law Advocates), outreach and potential research (SSA, Justice in Aging, National Disability Rights Center, National Consumer Law Center) |  | Beverly.yang@cfpb.gov
Proposed New Action | Older Americans | CFPB seeks to understand the consumer financial protection risks that people seeking LTSS face in the marketplace for residential care, personally identifiable information, and financial products. To this end, the CFPB is holds regular listening sessions with stakeholders such as the Consumer Voice, National Academy of Elder Law Advocates, and Leading Age. We also plan to engage in small-scale qualitative research (FY24). |  | Beverly.yang@cfpb.gov
Proposed New Action

## CMS New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action | CMS | CMS[JS1] ’ CCSQ hospice team will propose information and an educational video about the hospice complaint process for beneficiary awareness to be considered for a forthcoming Medicare & You handbook. The information states “If you have concerns about the quality of care you or a loved one received in a state or federally-certified healthcare facility, you may file a formal complaint directly with your state's survey agency. For a list of State Survey Agency Web site addresses and phone numbers that may help you with the filing of your complaint, use the following link, https://www.cms.gov/medicare/provider-enrollment-and-certification/surveycertificationgeninfo/contactinformation . CMS has also created a 10-minute video overview of the complaint process: https://www.youtube.com/watch?v=-eEZNWOLYZE . In addition to contacting your state’s survey agency, you can file a complaint with your Beneficiary and Family Centered Care Quality Improvement Organization (BFCC-QIO) by visiting Medicare.gov/claims-appeals/filea-complaint-grievance/filing-a-complaint-about-your-quality-of-care or calling 1-800-MEDICARE (1-800-633-4227). TTY users can call 1-877-486-2048.” |  | Jodie Sumeracki NOTE: | Status: Complete. CCSQ hospice team submitted this information for inclusion in May 2023. They also noted that the Medicare Handbook helps identify beneficiaries’ relevant caregiver resources. The CMS Hospice Handbook [JS1] further identifies these resources for family and caregivers which was updated in CY2022 (https://www.medicare.gov/Pubs/pdf/02154-medicare-hospice-benefits.pdf) . We note that hospice conditions of participation at 42 CFR Part 418, strongly support the education and inclusion of the family caregiver and see the family caregiver as an integral recipient of care and support.
Proposed New Action |  | [JS1]NEW Submission |  |  | [JS1]ACL – Thomas noted this in his comments. Take a look and see if you think this is something we could/should capture in other area of the strategy as a completed action, even though it was not originally proposed.
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## DOE New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]” | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## DOL New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action | Women's Bureau | WB is working with BLS to fund and support the 2024 Leave and Job Flexibilities Module in the American Time Use Survey. |  | Jonathan Katz, katz.jonathan.p@dol.gov
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## FEMA New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## HRSA New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action | HRSA | HRSA will continue to support its webpage on caregiving to achieve GOAL 1 of the Strategy in 2023. |  | joan Weiss, jweiss@hrsa.gov
Proposed New Action | HRSA | HRSA will continue to have a caregiver representative on its Advisory Committee on Interdisciplinary, Community-Based Linkages to achieve GOAL 1 of the Strategy in 2023.
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action | HRSA | HRSA will support training of family caregivers by Geriatrics Workforce Enhancement Program (GWEP) and Geriatrics Academic Career Awards (GACA) Program in 2023. This training will show family caregivers how to be a central component of the interdisciplinary care team and how to access long-term services and supports in order to achieve the goal of RAISE GOAL 1 in 2023. |  | Joan Weiss, jweiss@hrsa.gov
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action | HRSA | HRSA will continue to include a caregiver representative on its Advisory Committee on Interdisciplinary, Community-Based Linkages in 2022 in support of GOAL 1 of the Strategy. |  | joan Weiss, jweiss@hrsa.gov
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action | HRSA | HRSA will continue to provide support to GWEP grant recipients and their partners to include family caregivers in their education and training activities in support of GOAL 1 of the Strategy. |  | Joan Weiss, jweiss@hrsa.gov
Proposed New Action
Proposed New Action

## NIA New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## VA New Actions (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## New Agency A (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## New Agency B (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action

## New Agency C (hidden)
Goal 1 Proposed New Actions
Outcomes/ New Actions | Lead Agency Division/Office | Action Description: "[In/by (insert timeframe), (agency/division/office name) will (insert action) to achieve the goal of (insert outcome)]”. | Cross Linkage to | Submitted By (Name, Contact Info)
Outcome 1.1: Americans are educated about and understand the experience of family caregiving.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.2: Caregiver self-identification and knowledge of services is enhanced.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.3: Outreach to family caregivers is improved.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.4: Family caregiving—and caregivers—are embedded in federal, state, territorial, tribal, and local planning.
Proposed New Action
Proposed New Action
Proposed New Action
Outcome 1.5: Public-private partnerships at all levels help drive family caregiver recognition and support.
Proposed New Action
Proposed New Action
Proposed New Action